## Sheet1
Potential issue if we open source RIGHT NOW	Probability	Impact	Weighted	Details	Short-term mitigation	Long-term mitigation
Press release puts pressure on installation being simple	3	1	0.6	We deploy Wharf with Wharf today. Not optimal. Wharf lacks an installation guide. / Though this is not to gain adoption, we already have customers with Wharf installed.	Make Helm chart more plug and play. Document installation guide. Document Jenkins setup or ignore that?	Dropping Jenkins will make installation even easier
Bad ticket management integration with other departments	5	1	1	We’re aiming for using GitHub Issues, while the rest of the company will use Spark. / We’ve already discussed the “confidential data” part of issues, and concluded it’s fine to leave that data out. It’s not required to complete a task.	Ignore it until someone complains	Take complaints into consideration. MAYBE think about adding Spark↔GitHub Issues integration or other solutions
Open sourcing before dropping Jenkins leads to locking into Jenkins	2	2	0.8	We get comfy with having Jenkins, postponing and down-prioritizing its replacement more and more	Bite the sour apple and work on it. Can we have Jenkins and Wharf cmd side by side until Wharf cmd is up to speed? / Same API schema, so we can revert anyway if things break
Our reputation is damaged if Wharf is bad	3	1	0.6	Releasing a bad product is never good for reputation	Swallow our pride. Actually most OSS is bad when it’s initially released. OSS is not about the “blame-game”. / Add “BETA” to the name?	Improve Wharf as time goes on.
Lots of work to transfer WO’s	5	2	2	We plan on using GitHub Issues & Projects instead of Cure or Spark.	We’re talking < 80 WO’s. Can be done in just a few hours if we team up.	One time thing.
Forced upon backward compatibility	3	4	2.4	We do have a lot of backward incompatible changes planned. Ex: dropping Jenkins & reworking API endpoints	Define and document backward compatibility policy. Ex: 1 major back. RFC? / Not really related to us open sourcing though…
Wharf does not support GitHub.com yet	4	3	2.4	Cannot build Wharf’s Docker images via GitHub yet	Mirror repos to our GitLab instance	Fix wharf-provider-github (lots of unknowns for getting it to work)

					GET /v1/projects
					GET /projects?apiVersion=2
	1	1	0.2		Content-Type=application/wharf-v1.2+json
	2	1	0.4
	3	1	0.6
	4	1	0.8
	5	1	1
	1	2	0.4
	2	2	0.8
	3	2	1.2
	4	2	1.6
	5	2	2
	1	3	0.6
	2	3	1.2
	3	3	1.8
	4	3	2.4
	5	3	3
	1	4	0.8
	2	4	1.6
	3	4	2.4
	4	4	3.2
	5	4	4
	1	5	1
	2	5	2
	3	5	3
	4	5	4
	5	5	5